## START HERE
CONTRACTOR PROFIT TOOLKIT ¦ 1.2
STEP | WHAT TO DO | IMPORTANT DETAIL
01 | Enter project name, overhead budget and contingency on Project Setup. | All demo numbers are fictional and must be replaced.
02 | Build your base quote in Estimate with quantities, costs and markups. | Markup is a percentage of COST, not sales margin.
03 | Log every real expense ONCE in Actual Costs. | Include approved change-order expenses here; do not separately add change-order estimated costs to actuals.
04 | Track changes in Change Orders and mark their actual status. | Only Approved changes increase contracted revenue.
05 | Enter customer payments in Payments. | Revenue contracted is not the same thing as money collected.
06 | Review Dashboard warnings and contribution margins. | Incomplete job costs overstate profit. Receipts less incurred costs is NOT cash flow.
07 | Use USD; enter dates as real Excel dates. | Customer tax excluded. Costs include nonrecoverable purchase taxes. Negative payment = refund.
08 | Duplicate this workbook per project. | Fixed capacity: 100 estimate, 200 costs, 100 changes, 100 payment rows. Do not add rows.
09 | Check unusual expense classifications and pending changes. | Spreadsheet is a management aid, not tax, legal, accounting or certified estimating advice.
10 | Store your files securely and back up regularly. | Edit blue cells. Sheet protection prevents accidents, not unauthorized access. No password needed to unprotect.

## Project Setup
PROJECT SETUP ¦ EDIT BLUE CELLS
FIELD | VALUE | NOTES
Project name |  | Replace before production use
Client name |  | Replace with your client
Project ID |  | One project per workbook
Estimated direct overhead ($) | 0 | Project-attributable supervision, permits, overhead; not included in Estimate direct line items
Actual overhead incurred ($) | 0 | Enter project-attributable overhead already incurred; exclude amounts also logged under Actual Costs
Contingency rate | 0% | Contingency is a planning reserve; not income or an actual expense
Sales tax allowance ($) | 0 | Excluded informational allowance. Enter all other figures consistently net of customer sales tax.
Notes |  | Use local applicable rules and your accountant
Reporting date |  | As-of date used for illustrative tracking
Target contribution margin | 20% | Benchmark after project overhead; excludes unallocated company overhead and tax.

## Estimate
BASE ESTIMATE ¦ DIRECT LINE-ITEM COSTS
LINE ITEM | CATEGORY | QUANTITY | UNIT COST ($) | DIRECT COST ($) | MARKUP % | SELL PRICE ($) | NOTES

## Actual Costs
ACTUAL COST LEDGER ¦ ENTER EACH COST ONCE
DATE | DESCRIPTION | CATEGORY | QTY | UNIT COST ($) | ACTUAL COST ($) | REFERENCE | BASE / CHANGE

## Change Orders
CHANGE ORDERS ¦ APPROVED REVENUE ONLY
CHANGE ID | DESCRIPTION | STATUS | ADDED REVENUE ($) | EST. CHANGE COST ($) | EST. CONTRIBUTION ($) | NOTES
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Payments
PAYMENTS RECEIVED ¦ CASH ACTUALLY COLLECTED
DATE | PAYMENT REFERENCE | AMOUNT RECEIVED ($) | PAYMENT METHOD | NOTES

## Dashboard
PROJECT DASHBOARD ¦ ONE JOB AT A TIME
METRIC | VALUE | WHAT THIS MEANS
Base quoted revenue | 0 | Base quoted selling prices, excluding pending changes
Approved change revenue | 0 | Only approved changes count as contract revenue
Contracted revenue | 0 | Base revenue plus approved change orders; not cash collected
Estimated base direct costs | 0 | Estimated direct costs from base estimate
Estimated approved change costs | 0 | Estimates only; NOT added to actual costs
Budgeted project overhead | 0 | Planned overhead directly attributable to this project
Estimated total cost | 0 | Estimated base direct + approved change + overhead
Budgeted job contribution | 0 | Contract revenue less estimated direct costs and attributable overhead; excludes corporate overhead and taxes.
Budgeted margin |  | Contribution / contracted revenue. Blank when revenue is zero; markup is cost-based.
Logged actual direct cost | 0 | All actual cost entries, including change work where incurred
Actual overhead incurred | 0 | Actual attributable overhead not already logged above
Total incurred costs | 0 | Costs incurred to date; incomplete projects omit future costs
Contract less costs incurred | 0 | Not final profit if job is incomplete or unbilled costs remain
Incurred-cost margin |  | Provisional contribution / contract. Blank when revenue is zero; no completion forecast.
Customer payments received | 0 | Actual money collected from customer
Uncollected contract balance | 0 | Negative means receipts exceed contract. Not accounts receivable or an invoice aging report.
Receipts less incurred costs | 0 | NOT cash flow: expenses may be unpaid. No expense-payment ledger is included.
Cost still available vs budget | 0 | Negative means incurred costs exceed total estimated budget
Contingency allowance | 0 | Optional planning reserve, NOT automatically added to contracted revenue
Margin target | 20% | Desired project margin; assess again when the job is complete
Entry warnings | 0 | Missing required numeric fields on described entries. Counts fields, not rows. Review before relying on totals.
IMPORTANT | Revenue is contracted, not necessarily invoiced or collected.
COST POLICY | Change-order actual costs belong in Actual Costs exactly once.
STATUS | Provisional until every cost is recorded. Blank margin means zero contract revenue.

## RELEASE NOTES
CONTRACTOR TOOLKIT — RELEASE NOTES
Version | 1.2 production package
Scope | Single project per workbook; USD; Excel formulas
Demo data | All example customers and transactions are fictional
Profit warning | Projected margin is not realized profit; verify all costs and revenue
Tax warning | No sales tax, income tax, payroll tax or jurisdiction-specific compliance calculated
License | One purchasing business may reuse for its own jobs. No redistribution or resale. See included license.