## START HERE
CONTRACTOR PROFIT TOOLKIT ¦ 1.2
STEP | WHAT TO DO | IMPORTANT DETAIL
01 | Enter project name, overhead budget and contingency on Project Setup. | All demo numbers are fictional and must be replaced.
02 | Build your base quote in Estimate with quantities, costs and markups. | Markup is a percentage of COST, not sales margin.
03 | Log every real expense ONCE in Actual Costs. | Include approved change-order expenses here; do not separately add change-order estimated costs to actuals.
04 | Track changes in Change Orders and mark their actual status. | Only Approved changes increase contracted revenue.
05 | Enter customer payments in Payments. | Revenue contracted is not the same thing as money collected.
06 | Review Dashboard warnings and contribution margins. | Incomplete job costs overstate profit. Receipts less incurred costs is NOT cash flow.
07 | Use USD; enter dates as real Excel dates. | Customer tax excluded. Costs include nonrecoverable purchase taxes. Negative payment = refund.
08 | Duplicate this workbook per project. | Fixed capacity: 100 estimate, 200 costs, 100 changes, 100 payment rows. Do not add rows.
09 | Check unusual expense classifications and pending changes. | Spreadsheet is a management aid, not tax, legal, accounting or certified estimating advice.
10 | Store your files securely and back up regularly. | Edit blue cells. Sheet protection prevents accidents, not unauthorized access. No password needed to unprotect.

## Project Setup
PROJECT SETUP ¦ EDIT BLUE CELLS
FIELD | VALUE | NOTES
Project name | Sample: Electrical Fit-Out | Replace before production use
Client name | Sample Customer | Replace with your client
Project ID | DEMO-001 | One project per workbook
Estimated direct overhead ($) | 650 | Project-attributable supervision, permits, overhead; not included in Estimate direct line items
Actual overhead incurred ($) | 500 | Enter project-attributable overhead already incurred; exclude amounts also logged under Actual Costs
Contingency rate | 5% | Contingency is a planning reserve; not income or an actual expense
Sales tax allowance ($) | 0 | Excluded informational allowance. Enter all other figures consistently net of customer sales tax.
Notes | Fictional demonstration data | Use local applicable rules and your accountant
Reporting date | 2026-10-11 | As-of date used for illustrative tracking
Target contribution margin | 20% | Benchmark after project overhead; excludes unallocated company overhead and tax.

## Estimate
BASE ESTIMATE ¦ DIRECT LINE-ITEM COSTS
LINE ITEM | CATEGORY | QUANTITY | UNIT COST ($) | DIRECT COST ($) | MARKUP % | SELL PRICE ($) | NOTES
EMT conduit 3/4in | Materials | 200 | 1.85 | 370 | 25% | 462.5 | Fictional demo
THHN conductors | Materials | 650 | 0.48 | 312 | 25% | 390 | Fictional demo
Electrician labor | Labor | 38 | 52 | 1976 | 35% | 2667.6 | Loaded cost assumption
Helper labor | Labor | 22 | 32 | 704 | 35% | 950.4 | Loaded cost assumption
Equipment rental | Equipment | 2 | 175 | 350 | 20% | 420 | Fictional demo

## Actual Costs
ACTUAL COST LEDGER ¦ ENTER EACH COST ONCE
DATE | DESCRIPTION | CATEGORY | QTY | UNIT COST ($) | ACTUAL COST ($) | REFERENCE | BASE / CHANGE
2026-10-01 | EMT conduit purchased | Materials | 220 | 1.95 | 429 | Receipt 001 | Base
2026-10-02 | THHN wire purchased | Materials | 680 | 0.5 | 340 | Receipt 002 | Base
2026-10-05 | Electrician hours | Labor | 41 | 52 | 2132 | Timesheet 01 | Base
2026-10-05 | Helper hours | Labor | 20 | 32 | 640 | Timesheet 01 | Base
2026-10-06 | Lift rental | Equipment | 2 | 190 | 380 | Rental 001 | Base

## Change Orders
CHANGE ORDERS ¦ APPROVED REVENUE ONLY
CHANGE ID | DESCRIPTION | STATUS | ADDED REVENUE ($) | EST. CHANGE COST ($) | EST. CONTRIBUTION ($) | NOTES
CO-001 | Extra receptacles | Approved | 450 | 225 | 225 | Fictional demo; actual cost must be logged in Actual Costs if incurred
CO-002 | Panel label changes | Pending | 250 | 100 | 0 | Excluded from contracted revenue
CO-003 | Added conduit run | Rejected | 300 | 175 | 0 | Excluded from contracted revenue
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Payments
PAYMENTS RECEIVED ¦ CASH ACTUALLY COLLECTED
DATE | PAYMENT REFERENCE | AMOUNT RECEIVED ($) | PAYMENT METHOD | NOTES
2026-10-07 | Deposit-001 | 1500 | Bank transfer | Fictional demo
2026-10-10 | Progress-001 | 1000 | Bank transfer | Fictional demo

## Dashboard
PROJECT DASHBOARD ¦ ONE JOB AT A TIME
METRIC | VALUE | WHAT THIS MEANS
Base quoted revenue | 4890.5 | Base quoted selling prices, excluding pending changes
Approved change revenue | 450 | Only approved changes count as contract revenue
Contracted revenue | 5340.5 | Base revenue plus approved change orders; not cash collected
Estimated base direct costs | 3712 | Estimated direct costs from base estimate
Estimated approved change costs | 225 | Estimates only; NOT added to actual costs
Budgeted project overhead | 650 | Planned overhead directly attributable to this project
Estimated total cost | 4587 | Estimated base direct + approved change + overhead
Budgeted job contribution | 753.5 | Contract revenue less estimated direct costs and attributable overhead; excludes corporate overhead and taxes.
Budgeted margin | 14.11% | Contribution / contracted revenue. Blank when revenue is zero; markup is cost-based.
Logged actual direct cost | 3921 | All actual cost entries, including change work where incurred
Actual overhead incurred | 500 | Actual attributable overhead not already logged above
Total incurred costs | 4421 | Costs incurred to date; incomplete projects omit future costs
Contract less costs incurred | 919.5 | Not final profit if job is incomplete or unbilled costs remain
Incurred-cost margin | 17.22% | Provisional contribution / contract. Blank when revenue is zero; no completion forecast.
Customer payments received | 2500 | Actual money collected from customer
Uncollected contract balance | 2840.5 | Negative means receipts exceed contract. Not accounts receivable or an invoice aging report.
Receipts less incurred costs | -1921 | NOT cash flow: expenses may be unpaid. No expense-payment ledger is included.
Cost still available vs budget | 166 | Negative means incurred costs exceed total estimated budget
Contingency allowance | 229.35 | Optional planning reserve, NOT automatically added to contracted revenue
Margin target | 20% | Desired project margin; assess again when the job is complete
Entry warnings | 0 | Missing required numeric fields on described entries. Counts fields, not rows. Review before relying on totals.
IMPORTANT | Revenue is contracted, not necessarily invoiced or collected.
COST POLICY | Change-order actual costs belong in Actual Costs exactly once.
STATUS | Provisional until every cost is recorded. Blank margin means zero contract revenue.

## RELEASE NOTES
CONTRACTOR TOOLKIT — RELEASE NOTES
Version | 1.2 production package
Scope | Single project per workbook; USD; Excel formulas
Demo data | All example customers and transactions are fictional
Profit warning | Projected margin is not realized profit; verify all costs and revenue
Tax warning | No sales tax, income tax, payroll tax or jurisdiction-specific compliance calculated
License | One purchasing business may reuse for its own jobs. No redistribution or resale. See included license.